## Slide 1
Supply Chain Compliance:
Delayed Component Risk
Review and Remediation Plan
Components CARB123, BIND567, and COAT890 — Performance Analysis and Corrective Action
Prepared by Justin Quinones | August 2026
Compliance Review
Notes: Welcome and frame the purpose: a compliance review of three delayed components — CARB123, BIND567, COAT890.
Scope covers delivery performance against a 95% on-time target, root causes, and a corrective action plan.
Findings are drawn from the Task 3 supply chain analysis and the expanded metrics dataset.
Ask for executive sponsor decisions at the end — Phase 1 launch needs sign-off.

## Slide 2
Summary of Key Issues
Three components are underperforming against a 95% on-time delivery target, creating measurable compliance and production risk. [1]
Combined On-Time Delivery Rate
88.1%
10 records
Target
95%
−6.9 pts below target
Source: Task 3 Supply Chain Analysis Report.docx
COAT890 Highest Priority
84.2% on-time rate across 5 records; multi-supplier dependency with recurring mitigations — signals an unresolved systemic issue
CARB123 Moderate Risk
90.25% on-time across 4 records; inconsistent risk classifications and mitigation approaches reduce auditability
BIND567 Planning Risk
99% on-time but 64-day delivery timeline and 26-day lead-time variance create significant planning and disruption exposure
Cross-cutting drivers: supplier variability, forecast misalignment, and inconsistent exception handling are elevating compliance risk across all three components
Notes: Headline: combined on-time rate is 88.1%, 6.9 points below the 95% target across 10 records.
COAT890 is highest priority at 84.2% with multi-supplier dependency and repeat mitigations.
CARB123 sits at 90.25% — the bigger concern is inconsistent risk classification, not the rate itself.
BIND567 hits 99% but a 64-day cycle and 26-day variance create planning exposure.
Common threads: supplier variability, forecast misalignment, inconsistent exception handling.

## Slide 3
Component Performance Snapshot
Each component presents a distinct risk profile requiring a tailored response. [1]
Source: Task 3 Supply Chain Analysis Report.docx
Lowest delivery rate (84.2%) across 5 records; multi-supplier dependency with fragmented coordination
COAT890 — Highest Priority
99% on-time masks a 64-day cycle with 26-day variance — any disruption has extended recovery window
BIND567 — Long-Cycle Exposure
90.25% on-time but inconsistent risk classifications across records reduce auditability
CARB123 — Mixed Risk Profile
Component | Supplier(s) | On-Time Rate | Avg Delivery | Lead-Time Variance | Priority
CARB123 | RawMatPlus | 90.25% | 23.25 days | 10.5 days | Medium
BIND567 | EcoSupply | 99% | 64 days | 26 days | Medium
COAT890 | GlobalChem, RawMatPlus, NextGen Pharma | 84.2% | 21.2 days | 8.2 days | High
Notes: Walk the table left to right — supplier concentration, rate, cycle time, variance, priority.
Emphasize each component has a distinct risk profile, so responses must be tailored.
COAT890: lowest rate and three suppliers with fragmented coordination.
BIND567: high rate masks long-cycle exposure — recovery from any disruption is slow.
CARB123: acceptable rate, weak auditability.

## Slide 4
On-Time Delivery Rate by Component vs. 95% Target
Source: Expanded_SupplyChainMetrics.xlsx
Data Insights from Excel Analysis
The Expanded Supply Chain Metrics dataset reveals recurring delivery failures and inconsistent mitigation execution across all three components. [2]
COAT890
falls 10.8 percentage points below the 95% target — the largest delivery gap of the three components.
CARB123
falls 4.75 points below target; inconsistent risk classifications across records undermine auditability.
BIND567
meets rate target but carries a 26-day lead-time variance — the highest across all components, creating planning exposure.
Mitigations repeat
across COAT890 records (alternate sourcing, expedited shipping, contract review) — signal of unresolved root cause.
Data gap:
Defect rates and quality pass rates not in performance scoring — understating true compliance exposure.
Chart: Component
| CARB123 | BIND567 | COAT890
On-Time Delivery Rate (%) | 90.25 | 99 | 84.2
95% Target | 95 | 95 | 95
Notes: Chart shows performance versus the 95% target line — COAT890 is 10.8 points below.
CARB123 trails by 4.75 points; documentation inconsistency compounds the gap.
BIND567 clears the rate target but carries the highest lead-time variance at 26 days.
Repeating mitigations on COAT890 indicate an unresolved root cause, not isolated incidents.
Flag the data gap: defect and quality pass rates are excluded from scoring, understating exposure.

## Slide 5
Root Cause Analysis
Delivery underperformance traces to three structural causes: fragmented supplier coordination, reactive risk management, and long-cycle planning misalignment. [1]
CARB123
RawMatPlus
Inconsistent planning assumptions across records
Varying risk ratings — no standardized assessment criteria
Reactive mitigation rather than a documented, repeatable protocol
BIND567
EcoSupply
64-day long-cycle dependency with insufficient buffer alignment
26-day lead-time variance not absorbed by current safety stock
Single-record dataset limits trend visibility and risk detection
COAT890
GlobalChem · RawMatPlus · NextGen Pharma
Fragmented multi-supplier coordination across three vendors
Forecast misalignment and inconsistent replenishment models
Differing execution capability across suppliers amplifies delivery risk
Cross-Cutting Issue
Exception handling (expedited shipments, alternate sourcing) lacks documented rationale, cost impact, or approval path — creating audit vulnerability across all three components.
Notes: Three structural causes: fragmented supplier coordination, reactive risk management, long-cycle misalignment.
COAT890's three vendors differ in execution capability and replenishment models.
BIND567's safety stock does not absorb its variance, and single-record data limits trend visibility.
CARB123 lacks standardized risk criteria, so ratings vary record to record.
Cross-cutting: exception handling has no documented rationale, cost impact, or approval path.

## Slide 6
Compliance Review
Compliance Implications
Delivery gaps and documentation weaknesses create measurable exposure across continuity of supply, traceability, supplier oversight, and quality release. [1]
Continuity of Supply
COAT890's 84.2% on-time delivery rate and multi-supplier dependency elevate production disruption risk if inventory buffers are insufficient.
High Priority
Traceability and Documentation
CARB123's inconsistent risk levels and mitigation actions across records undermine auditability and management review readiness.
Audit Exposure
Supplier Oversight
BIND567's 64-day delivery timeline and 26-day lead-time variance require formal monitoring despite its high on-time rate.
Requires Monitoring
Quality and Release Risk
Defect rates and quality inspection pass rates must be reviewed alongside delivery delays — expedited actions must not bypass quality controls.
Data Gap
Supply Chain Compliance Review — Components CARB123, BIND567, COAT890
Prepared by Justin Quinones | August 2026
Notes: Translate performance issues into compliance exposure across four areas.
Continuity of supply is the high-priority risk driven by COAT890's rate and supplier spread.
Traceability suffers from CARB123's inconsistent records — a management review weakness.
BIND567 requires formal monitoring despite strong on-time performance.
Stress that expedited actions must never bypass quality release controls.

## Slide 7
Proposed Solutions
Six targeted actions address the root causes and close the compliance gaps across all three components. [1]
1
Prioritize COAT890 Remediation
Establish a component-level recovery plan: align supplier commitments, confirm near-term inventory coverage, and set a 95% delivery rate target.
2
Formalize CARB123 Risk Treatment
Standardize decision criteria for expedited shipping, inventory increases, contract review, and negotiated terms to reduce inconsistency and improve audit trail.
3
Address BIND567 Long-Cycle Exposure
Increase safety stock or advance reorder timing to match the 64-day delivery cycle and absorb the 26-day lead-time variance.
4
Implement Recurring Supplier Scorecards
Track on-time delivery, defect rate, lead-time variance, quality pass rate, and forecast accuracy on a defined cadence.
5
Recalibrate Demand Planning
Use forecast accuracy and production usage rates to reset reorder points, order sizes, and safety stock levels across all three components.
6
Document Exception Handling
Require formal rationale, quality review, cost impact assessment, and approval path for every expedited shipment or alternate sourcing decision.
Source: Task 3 Supply Chain Analysis Report.docx
7
Notes: Six actions map directly to the root causes just presented.
Actions 1-3 are component-specific: COAT890 recovery, CARB123 risk treatment, BIND567 buffer adjustment.
Actions 4-6 are systemic: supplier scorecards, demand planning recalibration, exception documentation.
Scorecards should track delivery, defects, variance, quality pass rate, and forecast accuracy.
Confirm owners and cadence before moving to the timeline.

## Slide 8
Implementation Plan
A phased 90-day plan prioritizes immediate risk reduction for COAT890 while building durable governance structures for all components. [1]
Phase 1 — Immediate
Days 1–30
Stabilize & Contain
Phase 2 — Near-Term
Days 31–60
Standardize & Structure
Phase 3 — Structural
Days 61–90
Govern & Sustain
Owners: Supply Chain Operations, Procurement, Quality Assurance — executive sponsor sign-off required for Phase 1 launch
Prepared by Justin Quinones | August 2026
Launch COAT890 recovery plan; confirm inventory buffers
Initiate supplier alignment meetings with GlobalChem, RawMatPlus, and NextGen Pharma
Establish exception documentation template and approval workflow
Standardize CARB123 risk assessment criteria and mitigation decision framework
Increase BIND567 safety stock to align with 64-day delivery cycle
Issue supplier scorecard template and begin tracking
Complete demand planning recalibration for all three components
Conduct first formal supplier scorecard review; establish recurring governance cadence
Close quality data gap — integrate defect rate and pass rate into performance reporting
Notes: Phased 90-day plan balancing immediate containment with durable governance.
Days 1-30 stabilize COAT890, confirm buffers, and open supplier alignment discussions.
Days 31-60 standardize CARB123 criteria, raise BIND567 stock, and roll out scorecards.
Days 61-90 recalibrate demand planning, run the first scorecard review, and close the quality data gap.
Ask for executive sponsor sign-off to launch Phase 1.

## Slide 9
References
[1] Task 3 Supply Chain Analysis Report.docx
[2] Expanded_SupplyChainMetrics.xlsx
Notes: Sources: the Task 3 supply chain analysis report and the expanded supply chain metrics dataset.
Offer to share the underlying records and calculations on request.
Close by inviting questions and confirming next steps and owners.